## Jira
Number | Epic | Story | Sub-Task | Status | Edge Cases | MVP | Comment
1 | Customer Features | Customer Signup & Login | Implement email and phone-based signup with AWS OTP verification | Complete | No | Yes | No Libyan OTP verification integrated yet.
2 | Customer Features | Customer Signup & Login | Develop profile management (update password, email, phone) | Complete |  | Yes | Need to connect with aws cognito for password update & reset
3 | Customer Features | Customer Signup & Login | Implement role-based access control (Customer, Service Provider, Admin) | Complete |  | Yes
4 | Customer Features | Home Address Management | Develop feature for users to add/edit home addresses | Complete |  | Yes
5 | Customer Features | Home Address Management | Integrate Google Maps API for geolocation and autofill | In Progress |  | Yes
6 | Customer Features | Home Screen | Develop browsing and search functionality by service category | Complete |  | Yes
7 | Customer Features | Home Screen | Create dynamic promotional banners | Complete |  | Yes
8 | Customer Features | Job Scheduling | Implement calendar-based date and time picker | Complete |  | Yes
9 | Customer Features | Job Scheduling | Enable immediate and scheduled booking functionality | Complete | Yes | Yes
10 | Customer Features | Booking Process | Develop detailed service description screens | Complete |  | Yes
11 | Customer Features | Booking Process | Have a service radius that includes the booking location | Complete | Yes
12 | Customer Features | Booking Process | Implement pricing calculation | Complete | No | Yes
13 | Customer Features | Booking Process | Add Hadith quotes on ethics for workers | not started |  | Yes
14 | Customer Features | Booking Process | Address management at checkout | In Progress |  | Yes
15 | Customer Features | Booking Process | Price Breakdown | Complete |  | Yes
16 | Customer Features | Booking Process | Confirmation Screen | Complete |  | Yes
17 | Customer Features | Booking Process | Email Confirmation | not started |  | Yes
18 | Customer Features | Booking Process | Allow users to select service-specific add-ons | Complete |  | Yes
19 | Customer Features | Promotions and Discounts | Develop feature for promo code application | Complete |  | Yes
20 | Customer Features | User Bookings Management | Create dashboard for viewing active, upcoming, and past bookings | Complete |  | Yes
21 | Customer Features | User Bookings Management | Enable users to modify schedules and addresses | Complete
22 | Customer Features | User Bookings Management | Built in contact or chat functionality | not started
23 | Customer Features | Review and Rating System | Develop functionality for users to leave reviews and ratings | Complete
24 | Customer Features | Notifications | Implement notifications for job status updates and promotions | Complete
25 | Customer Features | Service History | Enable viewing of past services | Complete
26 | Customer Features | User Profiles | Profile should update users table in cognito aws along with changing password, ability to add multiple phone numbers, primary/secondary | not started
27 | Customer Features | Arabic Language Support | Set default language based on device settings | not started
28 | Service Provider Features | Service Provider Signup & Login | Implement AWS OTP verification for providers | not started
29 | Service Provider Features | Service Provider Signup & Login | Service Provider Vetting Screen | not started
30 | Service Provider Features | Service Provider Signup & Login | Develop approval/rejection workflow for service providers | not started
31 | Service Provider Features | Profile Management | Allow providers to update personal information and services offered | Complete
32 | Service Provider Features | Job Management | Enable providers to view, accept, or decline job requests | Complete
33 | Service Provider Features | Job Management | Instant notifications for job offers or changes in schedules from customers | In Progress
34 | Service Provider Features | Ratings & Reviews | Allow providers to view average ratings and reviews | In Progress
35 | Administrative Features | User & Provider Management | Enable admins to CRUD user accounts | Complete
36 | Administrative Features | User & Provider Management | Enable admins to approve/reject provider accounts | Complete
37 | Administrative Features | Manage Service Categories and Pricing | Allow admins to CRUD service categories and sub-services | Complete
38 | Administrative Features | Promotional Banner Management | Enable admins to create dynamic banners linking to external sites | Complete
39 | Administrative Features | Discounts | Allow admins to configure promotional discounts and vouchers | Complete
40 | Administrative Features | Data Overview | Develop dashboard for admin statistics like revenue and job completion | In Progress
41 | Administrative Features | Security Features | Implement role-based access control and granular permissions | not started
42 | Technical Features | API Endpoints | RESTful API architecture | Complete
43 | Technical Features | API Endpoints | Comprehensive error handling | Complete
44 | Technical Features | API Endpoints | Status code standardization | Complete
45 | Technical Features | API Endpoints | Authentication middleware | Complete
46 | Technical Features | Service Provider API | CRUD operations for provider management | Complete
47 | Technical Features | Service Provider API | Availability management | Complete
48 | Technical Features | Service Provider API | Location updates | Complete
49 | Technical Features | Service Provider API | Booking management | Complete
50 | Technical Features | Service Provider API | Review system integration | Complete
51 | Product Bugs | Fix Booking and Review Issues | Resolve issues related to booking functionality and review visibility to ensure a seamless user experience.
52 | Product Bugs | Address Management Issues | Ensure users can add, update, and view their addresses correctly.
53 | Product Bugs | Admin Panel | Fix Custom Fields Update Issue
54 | Product Bugs | Admin Panel | Add Missing CRUD Operations:
55 | UI/UX

## Bugs
Number | Epic | Story | Sub-Task | Bug Detail
14 | Customer Features | Booking Process | Address management at checkout | The guest sign up - The address flow needs to be fixed for when a guest orders a service. Although the customer is able to add the address after sign up manually , they are unable to complete the service booking due to a bug which the app not recognising the address input.
23 | Customer Features | User Bookings Management | Create dashboard for viewing active, upcoming, and past bookings

## Edge Caese
Feature | Story | Edge Cases | Options
Customer Features | Booking Process | If all providers within a reasonable radius are unavailable, expand the search radius incrementally | Option 1: no service provider available (status: pending) Option 2: no service provider available in your radius location but we can charge you extra to come to your location (if a day ahead, but if last minute booking then say its unavailable please re-schedule?)
Customer Features | Booking Process | User switches between addresses while a booking is in progress, causing confusion in the system.
Customer Features | Booking Process | User accidentally cancels the claim of completion without realizing its impact.
Service Provider | Admin Panel | Service provider's service list does not sync with the admin's approved list.
Service Provider | Booking Process | Service provider selects a generic reason for declining, leaving admins unclear on specific issues.
Service Provider | Admin Panel | Uploaded pictures exceed the file size limit or unsupported formats are used.
Customer Features | Booking Process | Client fails to respond to additional information requests, delaying service fulfillment.
Service Provider | Admin Panel | A high success rate is displayed despite frequent declines due to manual overrides or system errors.
Service Provider | Booking Process | Two overlapping bookings occur when providers have short gaps in availability.
Service Provider | Booking Process | Pending service provider accounts remain unapproved due to admin oversight.
Service Provider | Admin Panel | Abusive or irrelevant messages are exchanged during communication.
Cancellation penalties are applied incorrectly or unfairly during system outages.
Admin accidentally disapproves an active listing, disrupting provider bookings.
Service providers add duplicate or conflicting services without admin knowledge.
Changes to personal details or rates are not reflected immediately, causing confusion.
Incomplete or inaccurate details are displayed for a booking in the history record.
Logging fails to capture all steps of the booking process, leading to incomplete data.
Admin actions are mislogged or omitted, causing discrepancies in workflow tracking.

## Hadith
1. The Honest Merchant
Arabic:
"التَّاجِرُ الصَّدُوقُ الأَمِينُ مَعَ النَّبِيِّينَ وَالصِّدِّيقِينَ وَالشُّهَدَاءِ."
English:
"The honest and trustworthy merchant will be with the Prophets, the truthful, and the martyrs."
(Jami` at-Tirmidhi, Hadith 1209)
2. Earning Honestly
Arabic:
"إِنَّ أَفْضَلَ مَا أَكَلَ الرَّجُلُ مِنْ كَسْبِهِ، وَإِنَّ نَبِيَّ اللَّهِ دَاوُدَ كَانَ يَأْكُلُ مِنْ كَسْبِ يَدِهِ."
English:
"The best food a man can eat is that which he has earned with his own hands. The Prophet Dawud (David) used to eat from what he earned with his own hands."
(Sunan al-Tirmidhi, Hadith 1357)
3. Safety from Harm
Arabic:
"الْمُسْلِمُ مَنْ سَلِمَ الْمُسْلِمُونَ مِنْ لِسَانِهِ وَيَدِهِ."
English:
"A Muslim is the one from whose tongue and hand the people are safe."
(Sahih al-Bukhari, Hadith 10)
4. Intentions
Arabic:
"إِنَّمَا الأَعْمَالُ بِالنِّيَّاتِ، وَإِنَّمَا لِكُلِّ امْرِئٍ مَا نَوَى."
English:
"Actions are judged by intentions, and every person will be rewarded according to their intention."
(Sahih Bukhari, Hadith 1)
5. Cheating is Forbidden
Arabic:
"مَنْ غَشَّنَا فَلَيْسَ مِنَّا."
English:
"He who cheats is not of us."
(Sahih Muslim, Hadith 102)
6. Fulfilling Trusts
Arabic:
"أَدِّ الأَمَانَةَ إِلَى مَنِ ائْتَمَنَكَ، وَلَا تَخُنْ مَنْ خَانَكَ."
English:
"Fulfill the trust of the one who entrusted you, and do not betray the one who betrayed you."
(Sunan Abu Dawood, Hadith 3535)
7. Striving for Livelihood
Arabic:
"إِنَّ اللَّهَ يُحِبُّ إِذَا عَمِلَ أَحَدُكُمْ عَمَلًا أَنْ يُتْقِنَهُ."
English:
"Allah loves to see His servant striving to earn a livelihood."
(Al-Mu’jam al-Awsat, Hadith 6071)
8. Controlling Anger
Arabic:
"لَيْسَ الشَّدِيدُ بِالصُّرَعَةِ، إِنَّمَا الشَّدِيدُ الَّذِي يَمْلِكُ نَفْسَهُ عِنْدَ الْغَضَبِ."
English:
"The strong is not the one who overcomes the people by his strength, but the strong is the one who controls himself while in anger."
(Sahih al-Bukhari, Hadith 6114)
9. Timely Payment
Arabic:
"أَعْطُوا الأَجِيرَ أَجْرَهُ قَبْلَ أَنْ يَجِفَّ عَرَقُهُ."
English:
"The wages of the worker must be paid before the sweat on his brow dries."
(Sunan Ibn Majah, Hadith 2443)
10. Cleanliness
Arabic:
"الطُّهُورُ شَطْرُ الإِيمَانِ."
English:
"Cleanliness is part of faith."
(Sahih Muslim, Hadith 223)
11. Equality of Mankind
Arabic:
"يَا أَيُّهَا النَّاسُ، أَلَا إِنَّ رَبَّكُمْ وَاحِدٌ، وَإِنَّ أَبَاكُمْ وَاحِدٌ، أَلَا لَا فَضْلَ لِعَرَبِيٍّ عَلَى أَعْجَمِيٍّ، وَلَا لِأَعْجَمِيٍّ عَلَى عَرَبِيٍّ، وَلَا لِأَحْمَرَ عَلَى أَسْوَدَ، وَلَا لِأَسْوَدَ عَلَى أَحْمَرَ إِلَّا بِالتَّقْوَى."
English:
"O people, your Lord is one, and your father (Adam) is one. There is no superiority of an Arab over a non-Arab, nor a non-Arab over an Arab, nor of a white over a black, nor a black over a white, except by piety."
(Musnad Ahmad, Hadith 22978)
12. Inner Character Matters:
Arabic:
"إِنَّ اللَّهَ لَا يَنْظُرُ إِلَى صُوَرِكُمْ وَأَمْوَالِكُمْ، وَلَكِنْ يَنْظُرُ إِلَى قُلُوبِكُمْ وَأَعْمَالِكُمْ."
English:
"Indeed, Allah does not look at your appearance or your wealth, but He looks at your hearts and deeds."
(Sahih Muslim, Hadith 2564)